## 2008 reseal
JOB NO. | LOCATION | Contract $ Amount | 50 % paid | Progress Billings paid | TOTAL PAID
497.11.05 | Reseal Luce @ White River | 11075 |  | 12081.58 | 12081.58
497.12.01 | Reseal Green north of 1 Mile | 7145 |  | 8594.61 | 8594.61
497.12.02 | Reseal Maplie Island b/w 4 and 6 Mile | 19900 |  | 12995.96 | 12995.96
497.23.07.2007 | Wedge and Reseal 110th b/w Oak and Paw Paw | 15675 |  | 11776.95 | 11776.95
497.23.16 | Wedge and Reseal 136th b/w Spruce and Willow | 23200 |  | 14902 | 14902
497.23.17 | Reseal Oak b/w 100th and 120th | 8325 |  | 7778.37 | 7778.37
497.23.18 | Reseal 104th between Willow and M-37 | 10350 |  | 5514.35 | 5514.35
497.24.13 | Wedge and Reseal 136th b/w Elm and Juniper | 41287.5 |  | 36009.91 | 36009.91
109653.73

## 2008 contracts
JOB NO. |  | LOCATION | Contract $ Amount | 50 % paid | Progress Billings paid | TOTAL PAID | Outstanding Billings | (OVER) UNDER CONTRACT $
488.03.02 |  | Grub, grade, and gravel Prospect and Marsh | 44200 | 0 | 31993.59 | 31993.59 |  | 12206.41
488.03.03 |  | Gravel, Grade and Pave Jerome starting at Township line and going North | 21500 | 0 | 10973 | 10973 |  | 10527
488.06.02 | 3/26/08 | Overlay Jerome Ave @ Nichols Lake | 27500 | 13750 | 6774.46 | 20524.46 |  | 6975.54
488.06.03 | 3/27/08 | Wedge and Overlay Lincoln between M-37 and Centerline | 32650 | 16325 | 14796.22 | 31121.22 |  | 1528.78
488.08.04 | 3/26/08 | Wedge and Overlay 6 Mile between Elm and Locust | 43600 | 21800 | 14427 | 36227 |  | 7373
488.08.05 | 3/26/08 | Wedge and Overlay Pine between 6 MI and Polk | 61400 | 30700 | 18383 | 49083 |  | 12317
488.08.06 | 5/28/08 | Wedge and Overlay 6 mile between Pine and Locust | 42100 |  | 20000 | 20000 | 15815.73 | 6284.27
488.08.07 | 5/28/08 | pulverized thebo | 750 |  | 750 | 750 |  | 0
488.09.04 | 3/26/08 | Wedge and Overlay Cypress Ave between 3 MI and 4 MI | 36600 | 18300 | 0 | 18300 |  | 18300
488.09.05 | 3/28/08 | Wedge and Overlay Cypress Ave between 4 MI and 5 Mile | 36600 |  | 31740.6 | 31740.6 |  | 4859.4
488.11.05 | 5/28/08 | Grub, Grade, and Gravel Baldwin starting @ 3 Mile and goIng North for approx. 1500 feet | 48560 | 24280 |  | 24280 |  | 24280
488.11.06 | 6/25/08 | Grub, Grade, and Gravel Baldwin starting @ 3 Mile and goIng North for approx. 1000' to address of 2795 | 25600 |  |  | 0 |  | 25600
488.12.03 | 2007-04-24 | Start at 7370 Jefferson and ditch going west | 6130 |  | 3923.11 | 3923.11 |  | 2206.89
488.12.04 | 2008-03-27 | Wedge and Overlay Adams from Fitzgerlad to Dickinson | 23800 | 11900 | 6690.41 | 18590.41 |  | 5209.59
488.12.05 | 2008-03-27 | Wedge and Overlay Madison & Fitzgerald between 5 MI and Adams | 48100 | 24050 | 18042 | 42092 |  | 6008
488.13.07 | 3/27/08 | Dith and install culvert on Comstock | 500 |  | 299.5 | 299.5 |  | 200.5
488.13.10 | 3/27/08 | Wedge and Overlay 44th between Green and Comstock | 43600 | 21800 | 15288.56 | 37088.56 |  | 6511.44
488.13.11 | 3/27/08 | Wedge and Overlay Dickinson from 40th to 48th | 42100 | 21050 | 15202 | 36252 |  | 5848
488.14.06 | 12/12/07 | Overlay Croswell between 16th and 24th | 44850 | 22425 | 15000 | 37425 | 1324.58 | 6100.42
488.14.07 | 12/12/07 | Overlay Crosweel between 8th and 16th | 36100 | 18050 | 14040.69 | 32090.69 |  | 4009.31
488.14.08 | 03/26/08 | Overlay Midway Dr @ Robinson Lake | 5750 | 2875 | 2600.52 | 5475.52 |  | 274.48
488.14.09 | 03/26/08 | Overlay Woodlawn @ Robinson Lake | 16950 | 8475 | 4604.13 | 13079.13 |  | 3870.87
488.14.10 | 03/26/08 | Overlay Oakland Dr @ Robinson Lake | 3750 | 1875 | 2174.24 | 4049.24 |  | -299.24
488.14.11 | 5/16/08 | Replace Culvert on 12th b/w Baldwin and Croswell | 1150 |  | 1150 | 1150 |  | 0
488.15.03 | 5-23-07 | Grub Grade, Gravel and Pave Walnut starting at 32nd and giong south for 2700 ft | 99304 | 33670 | 62083.91 | 95753.91 |  | 3550.09
488.15.04 | 5-23-07 | Pave & Shoulder Gravel Walnut Ave from 8th to 24th | ? |  |  | 0
488.15.05 | 5-23-07 | Grade, Gravel and Pave Walnut starting at 40th and giong north | 49080 |  | 45735.55 | 45735.55 |  | 3344.45
488.15.06 | 5-23-07 | Replace Culvert on 28th street east of Oak | 1000 |  | 915 | 915 |  | 85
488.17.19 | 6/16/08 | Grub, Grade, and Slage Lake Street From Tanowitz to End | 29780 |  | 3083 | 3083 |  | 26697
488.17.10 | 6/16/08 | Grub, Grade and Gravel 80th east of Beech | 69204 | 34602 | 21776.93 | 56378.93 |  | 12825.07
488.17.20 | 7/30/08 | Grub, Grade, Gravel Tannewitz between 92nd and Lake Street | 101738 |  |  | 0
488.18.03 | 4-16-08 | Grub, Grade and Gravel Oak between Croton and 56th | 130224 |  | 105199.62 | 105199.62 |  | 25024.38
488.19.04 |  | GGG and Pave 80th from Bingham to N. River | 280864 | 125432 | 93946.95 | 219378.95 |  | 61485.05
488.19.08 | 4-16-08 | Place GeoGrid 21AA Limestone | 54400 |  | 58413.62 | 58413.62 |  | -4013.62
488.19.09 | 4-16-08 | Grade and Slag Luce between 48th and 56th | 16800 |  | 17608.2 | 17608.2 |  | -808.2
488.20.04 | 3-27-08 | Wedge and Overlay Lake drive starting at Green and going east | 40600 |  | 37150.84 | 37150.84 |  | 3449.16
488.20.05 | 3/28/08 | Overlay with valley gutter, Lee Street and approx 400 feet of Chamberlian | 11200 | 5600 | 5925.56 | 11525.56 |  | -325.56
488.21.09 | 2/27/08 | Rebuild and Relocate intersection of Brucker and 112th | 31000 | 10241.37 | 9724 | 19965.37 |  | 11034.63
488.21.10 | 2/27/08 | Rebuild and Relocate intersection of 108th @ Green | 20000 | 9445.92 | 15096.18 | 24542.1 |  | -4542.1
488.22.06 | 4-24-07 | Grub, grade, gravel, pave Sand Beach Drive | 117200 | 58600 | 75631.52 | 134231.52 |  | -17031.52
488.22.10 | 11-28-07 | Grub, grade, gravel, pave 104th west of Croswell | 100772 | 50386 | 7605.95 | 57991.95 |  | 42780.05
488.23.15 | 6-7-08 | Grade and Pave 132nd St and Walnut | 90000 |  | 86115.72 | 86115.72 |  | 3884.28
488.24.10 | 12/12/07 | Grub, grade and gravel beech and butternut between 112th and 120th | 123368 | 61684 | 32063.32 | 93747.32 |  | 29620.68
488.24.11 | 12/12/07 | Wedge and Overlay 128th between Balsam and Butternut | 23850 | 11925 | 7572.86 | 19497.86 |  | 4352.14
488.24.12 | 1/23/08 | Grade, Gravel & Pave intersection of 128th and Butternut Ave | 12000 |  | 12511.7 | 12511.7 |  | -511.7
[6 empty] | 1606254.75 | 17140.31 | 371090.94

## 2012 Contracts
CURRENT 2012 TOWNSHIP PROJECTS
TOWNSHIP | PROJECT
LILLEY | Replace Culvert on Beaver Road East of Greenly
DENVER | Grade and Limestone Dickinson Avenue North of 4 Mile
EVERETT | Grade and Limeston 24th between Walnut and Spruce
CROTON | Grub, Grade and Gravel Cottonwood South of M-82
Grub, Grade and Gravel Cypress North of 56th Street
Grade, gravel and create leaching basin on El Camino Drive
GARFIELD | Wedge and Reseal 68th between Ferris and Centerline
Reseal Felch between N. River Drive and M-82
Grade, gravel and Pave Carol Street starting at Mundy and going East approximately 2,000 feet
BRIDGETON | Grade and Gravel 112th West of Warner
ASHLAND | Grub, Grade and Gravel Alger North of 112th
Ditch and place culverts on Wisner North of 104th and pave intersection
Grade, Gravel and Pave with Valley Gutter Easter and Lakeview
GRANT | Remove and replace culverts on 128th at Rogue River
ENSLEY | Grub, grade and gravel Hemlock Avenue between 123th and 128th and 128th between Hemlock and Pear Avenue
Wedge and Reseal 22 Mile between Elm and Locust
Reseal Elm between 128th and 136th
Grub, grade and gravel Elm between 112th and 120th
Reseal Butternut Ave between 120th and 128th
Reseal Oak and Balsam between 120th and 124th