## 2008 reseal
JOB NO. | LOCATION | Contract $ Amount | 50 % paid | Progress Billings paid | TOTAL PAID
497.11.05 | Reseal Luce @ White River | 11075 |  | 12081.58 | 12081.58
497.12.01 | Reseal Green north of 1 Mile | 7145 |  | 8594.61 | 8594.61
497.12.02 | Reseal Maplie Island b/w 4 and 6 Mile | 19900 |  | 12995.96 | 12995.96
497.23.07.2007 | Wedge and Reseal 110th b/w Oak and Paw Paw | 15675 |  | 11776.95 | 11776.95
497.23.16 | Wedge and Reseal 136th b/w Spruce and Willow | 23200 |  | 14902 | 14902
497.23.17 | Reseal Oak b/w 100th and 120th | 8325 |  | 7778.37 | 7778.37
497.23.18 | Reseal 104th between Willow and M-37 | 10350 |  | 5514.35 | 5514.35
497.24.13 | Wedge and Reseal 136th b/w Elm and Juniper | 41287.5 |  | 36009.91 | 36009.91
109653.73

## 2008 contracts
JOB NO. |  | LOCATION | Contract $ Amount | 50 % paid | Progress Billings paid | TOTAL PAID | Outstanding Billings | (OVER) UNDER CONTRACT $
488.03.02 |  | Grub, grade, and gravel Prospect and Marsh | 44200 | 0 | 31993.59 | 31993.59 |  | 12206.41
488.03.03 |  | Gravel, Grade and Pave Jerome starting at Township line and going North | 21500 | 0 | 10973 | 10973 |  | 10527
488.06.02 | 3/26/08 | Overlay Jerome Ave @ Nichols Lake | 27500 | 13750 | 6774.46 | 20524.46 |  | 6975.54
488.06.03 | 3/27/08 | Wedge and Overlay Lincoln between M-37 and Centerline | 32650 | 16325 | 14796.22 | 31121.22 |  | 1528.78
488.08.04 | 3/26/08 | Wedge and Overlay 6 Mile between Elm and Locust | 43600 | 21800 | 14427 | 36227 |  | 7373
488.08.05 | 3/26/08 | Wedge and Overlay Pine between 6 MI and Polk | 61400 | 30700 | 18383 | 49083 |  | 12317
488.08.06 | 5/28/08 | Wedge and Overlay 6 mile between Pine and Locust | 42100 |  | 20000 | 20000 | 15815.73 | 6284.27
488.08.07 | 5/28/08 | pulverized thebo | 750 |  | 750 | 750 |  | 0
488.09.04 | 3/26/08 | Wedge and Overlay Cypress Ave between 3 MI and 4 MI | 36600 | 18300 | 0 | 18300 |  | 18300
488.09.05 | 3/28/08 | Wedge and Overlay Cypress Ave between 4 MI and 5 Mile | 36600 |  | 31740.6 | 31740.6 |  | 4859.4
488.11.05 | 5/28/08 | Grub, Grade, and Gravel Baldwin starting @ 3 Mile and goIng North for approx. 1500 feet | 48560 | 24280 |  | 24280 |  | 24280
488.11.06 | 6/25/08 | Grub, Grade, and Gravel Baldwin starting @ 3 Mile and goIng North for approx. 1000' to address of 2795 | 25600 |  |  | 0 |  | 25600
488.12.03 | 2007-04-24 | Start at 7370 Jefferson and ditch going west | 6130 |  | 3923.11 | 3923.11 |  | 2206.89
488.12.04 | 2008-03-27 | Wedge and Overlay Adams from Fitzgerlad to Dickinson | 23800 | 11900 | 6690.41 | 18590.41 |  | 5209.59
488.12.05 | 2008-03-27 | Wedge and Overlay Madison & Fitzgerald between 5 MI and Adams | 48100 | 24050 | 18042 | 42092 |  | 6008
488.13.07 | 3/27/08 | Dith and install culvert on Comstock | 500 |  | 299.5 | 299.5 |  | 200.5
488.13.10 | 3/27/08 | Wedge and Overlay 44th between Green and Comstock | 43600 | 21800 | 15288.56 | 37088.56 |  | 6511.44
488.13.11 | 3/27/08 | Wedge and Overlay Dickinson from 40th to 48th | 42100 | 21050 | 15202 | 36252 |  | 5848
488.14.06 | 12/12/07 | Overlay Croswell between 16th and 24th | 44850 | 22425 | 15000 | 37425 | 1324.58 | 6100.42
488.14.07 | 12/12/07 | Overlay Crosweel between 8th and 16th | 36100 | 18050 | 14040.69 | 32090.69 |  | 4009.31
488.14.08 | 03/26/08 | Overlay Midway Dr @ Robinson Lake | 5750 | 2875 | 2600.52 | 5475.52 |  | 274.48
488.14.09 | 03/26/08 | Overlay Woodlawn @ Robinson Lake | 16950 | 8475 | 4604.13 | 13079.13 |  | 3870.87
488.14.10 | 03/26/08 | Overlay Oakland Dr @ Robinson Lake | 3750 | 1875 | 2174.24 | 4049.24 |  | -299.24
488.14.11 | 5/16/08 | Replace Culvert on 12th b/w Baldwin and Croswell | 1150 |  | 1150 | 1150 |  | 0
488.15.03 | 5-23-07 | Grub Grade, Gravel and Pave Walnut starting at 32nd and giong south for 2700 ft | 99304 | 33670 | 62083.91 | 95753.91 |  | 3550.09
488.15.04 | 5-23-07 | Pave & Shoulder Gravel Walnut Ave from 8th to 24th | ? |  |  | 0
488.15.05 | 5-23-07 | Grade, Gravel and Pave Walnut starting at 40th and giong north | 49080 |  | 45735.55 | 45735.55 |  | 3344.45
488.15.06 | 5-23-07 | Replace Culvert on 28th street east of Oak | 1000 |  | 915 | 915 |  | 85
488.17.19 | 6/16/08 | Grub, Grade, and Slage Lake Street From Tanowitz to End | 29780 |  | 3083 | 3083 |  | 26697
488.17.10 | 6/16/08 | Grub, Grade and Gravel 80th east of Beech | 69204 | 34602 | 21776.93 | 56378.93 |  | 12825.07
488.17.20 | 7/30/08 | Grub, Grade, Gravel Tannewitz between 92nd and Lake Street | 101738 |  |  | 0
488.18.03 | 4-16-08 | Grub, Grade and Gravel Oak between Croton and 56th | 130224 |  | 105199.62 | 105199.62 |  | 25024.38
488.19.04 |  | GGG and Pave 80th from Bingham to N. River | 280864 | 125432 | 93946.95 | 219378.95 |  | 61485.05
488.19.08 | 4-16-08 | Place GeoGrid 21AA Limestone | 54400 |  | 58413.62 | 58413.62 |  | -4013.62
488.19.09 | 4-16-08 | Grade and Slag Luce between 48th and 56th | 16800 |  | 17608.2 | 17608.2 |  | -808.2
488.20.04 | 3-27-08 | Wedge and Overlay Lake drive starting at Green and going east | 40600 |  | 37150.84 | 37150.84 |  | 3449.16
488.20.05 | 3/28/08 | Overlay with valley gutter, Lee Street and approx 400 feet of Chamberlian | 11200 | 5600 | 5925.56 | 11525.56 |  | -325.56
488.21.09 | 2/27/08 | Rebuild and Relocate intersection of Brucker and 112th | 31000 | 10241.37 | 9724 | 19965.37 |  | 11034.63
488.21.10 | 2/27/08 | Rebuild and Relocate intersection of 108th @ Green | 20000 | 9445.92 | 15096.18 | 24542.1 |  | -4542.1
488.22.06 | 4-24-07 | Grub, grade, gravel, pave Sand Beach Drive | 117200 | 58600 | 75631.52 | 134231.52 |  | -17031.52
488.22.10 | 11-28-07 | Grub, grade, gravel, pave 104th west of Croswell | 100772 | 50386 | 7605.95 | 57991.95 |  | 42780.05
488.23.15 | 6-7-08 | Grade and Pave 132nd St and Walnut | 90000 |  | 86115.72 | 86115.72 |  | 3884.28
488.24.10 | 12/12/07 | Grub, grade and gravel beech and butternut between 112th and 120th | 123368 | 61684 | 32063.32 | 93747.32 |  | 29620.68
488.24.11 | 12/12/07 | Wedge and Overlay 128th between Balsam and Butternut | 23850 | 11925 | 7572.86 | 19497.86 |  | 4352.14
488.24.12 | 1/23/08 | Grade, Gravel & Pave intersection of 128th and Butternut Ave | 12000 |  | 12511.7 | 12511.7 |  | -511.7
[6 empty] | 1606254.75 | 17140.31 | 371090.94

## 2012 Contracts
CURRENT 2013 TOWNSHIP PROJECTS
TOWNSHIP | PROJECT
GOODWELL | Wedge and Reseal 1 Mile b/w Cottonwood and Newcosta
DENVER | Wedge & Reseal MI b/w 4 Mile & Hesperia
Wedge & Reseal MI b/w 5 Mile & 6 Mil
DAYTON | Overlay Green between 20th and 24th
Wedge Comstock between 24th and 32nd
Wedge 32nd between Stone & Osborn
Wedge Comstock between 20th and 24th
SHERMAN | Overlay Luce at 24th and going South
Wedge Luce at 24th and going North
EVERETT | Grub, grade, gravel, Pave 16th b/w M-37 and Walnut
Wedge & Reseal 8th b/w Larch & Oak
CROTON | Wedge 80th between Locust and Pettit Lake Drive
Wedge and Overlay 52nd between Elm and Locust
Wedge and Reseal 56th between Croton & Newcosta
Wedge and Reseal Swan b/w M-82 & 86th b/w M-82 and Pear and Pear between 86th & 92nd b/w Pear and Elm
Wedge and Reseal Locust b/w 92nd and Township Line
BROOKS | Overlay Forest Lane between Clay and Catalpa
Overlay Clay south of 95th
Grade and Limestone Oak between Clay and Catalpa
Wedge Redwood starting at 88th and going south
Wedge and Reseal Summer South of 72nd
Wedge and Reseal Spruce N. of M-82
Wedge and Reseal Walnut b/w Croton Dr. and 72nd
Wedge and Reseal 72nd b/w Walnut and Summer
GARFIELD | Grub, grade, gravel & Pave Spring Drive b/w 68th & M-82
Grub, grade, gravel 80th b/w Baldwin & Croswell
Grub, grade, gravel 80th b/w Croswell and Luce
Grub, grade, gravel and Pave Felch between M-82 and Spring Drive
SHERIDAN | Reconstruct 56th Street between Warner & City Limits
BRIDGETON | GGG Fitzgerald south of South River Dr
ASHLAND | GGG Felch North of 104th
Overlay 116th at Wisner and going West
Wedge 104th at Felch
Wedge Felch at 104th Street
Wedge 136th at Wisner and going West for 8,500 ft
GRANT | Overlay 132nd between Elder and Willow
Wedge and Reseal 22 Mile between Thornapple & East Township Line
Wedge and Reseal Walnut north of 104th
Wedge and Reseal Thornapple between 136th & 22 Mile
Wedge and Reseal Poplar Ave between 128th & 136th
Wedge and Reseal Willow between 128th & 136th
Wedge and Reseal 128th between Spruce and Rogue River
Wedge and Reseal 136th West of Spruce
ENSLEY | GGG Elm b.w 112th and 120th
Pave w/ valley gutter Elm b/w 112th and 120th
Wedge and Reseal Balsam between 124th &128th
Wedge and Reseal Balsam b/w 124th & 128th
Wedge and Reseal 136th b/w Butternut and Beech
Wedge and Reseal 112th b/w Cottonwood and Cypress